## Features
Project: CoursesRoadmap
Team: 2
ID | Feature Name | Description | Remark
UC01 | Create, Edit, Delete Courses (Admin). | Create courses, Edit courses | Tester: PAKhoa
UC02 | View & Enroll & Post reviews Courses | View courses, Post comment for Courses | Tester: NTQuân
UC03 | View & Write story | View story, Post story, Share a course to Facebook | Tester: LNMNhật
UC04 | View & Edit user profile |  | Tester: PAKhoa
UC05 | View & Edit role for user |  | Tester: NTQuân

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01: Create, Edit, Delete Courses (Admin) | UC01
UC01 | UI1 | Create course | 1. Sign Up (Skip if you already have an account) 2. Login (username: "anhkhoa24082001@gmail.com", password: "123456") 3. Click "Admin Page" on navbar 4. Click "Course" in Admin Page 5. Click "Add course" | Admin create a course with detailed informationb | New course is displayed but not allowed to enter but must be edited | FAIL | PAKhoa | 2021-12-23
UC01 | UI2 | Edit course | 1. Sign Up (Skip if you already have an account) 2. Login (username: "anhkhoa24082001@gmail.com", password: "123456") 3. Click "Admin Page" on navbar 4. Click "Edit course" 5. Change Name of course 6. Click Save | Admin wants to change the name of the course | The course name has been changed but the application does not turn off the edit frame | FAIL | PAKhoa | 2021-12-23
UC01 | UI3 | Edit course | 1. Sign Up (Skip if you already have an account) 2. Login (username: "anhkhoa24082001@gmail.com", password: "123456") 3. Click "Admin Page" on navbar 4. Click "Edit course" 5. Change Name, Level, Catalog of course 6. Click Save | Admin wants to change Name, Level, Catalog of the course | The course name has been changed but the application does not turn off the edit frame | FAIL | PAKhoa | 2021-12-23
UC01 | UI4 | Edit course | 1. Sign Up (Skip if you already have an account) 2. Login (username: "anhkhoa24082001@gmail.com", password: "123456") 3. Click "Admin Page" on navbar 4. Click "Edit course" 5. Change Num Lesson of course 6. Click Save | Admin wants to changeNum lesson of the course | Admin can change course number to negative and the application does not turn off the edit frame | FAIL | PAKhoa | 2021-12-23
Function 02: View & Enroll & Post reviews Courses | UC02
UC02 | UI5 | Post a comment | 1. Sign Up (Skip if you already have an account) 2. Login (username: "quannguyenthanh558@gmail.com", password: "123456") 3. Click 1 course you want to comment 4. Fill the comment in comment area(content: "This is comment test") 5. Click "Post" icon | New comment with content "This is comment test", date is 14:00 - 23, Dec 2021, user: QuanBlue appeare in comment area | New comment do not appeare in comment | FAIL | NTQuân | 2021-12-23
UC02 | UI6 | Share course | 1. Sign Up (Skip if you already have an account) 2. Login (username: "quannguyenthanh558@gmail.com", password: "123456") 3. Click 1 course you want to share 4. Click "Share" button | Redirect to facebook page in new tab with share screen | Redirect to facebook page in new tab with share screen | Pass | NTQuân | 2021-12-23
UC02 | UI7 | Join course | 1. Sign Up (Skip if you already have an account) 2. Login (username: "quannguyenthanh558@gmail.com", password: "123456") 3. Click 1 course you want to join 4. Click "Join" button | Redirect to website contain this course | Nothing happen | FAIL | NTQuân | 2021-12-23
Function 03: View & Write story | UC03
UC03 | UI8 | View story | 1. Click "Story" on navbar | User want to view story | Can't display page "Story" | Pass | LNMNhật | 2021-12-23
UC03 | UI9 | Post story | 1. Sign Up (Skip if you already have an account) 2. Login (username: "lengocminhnhatntp@gmail.com", password: "123456") 3. Click "Story" on navbar 4. Write story in text field 5. Click Share | User wants to post story | The story has been posted on the page "Story" and there are no errors. | FAIL | LNMNhật | 2021-12-23
UC03 | UI10 | Share course to FACEBOOK | 1. Sign Up (Skip if you already have an account) 2. Login (username: "lengocminhnhatntp@gmail.com", password: "123456") 3. Click 1 course you want to share 4. Click "Share to Facebook" button | Redirect to facebook page in new tab with share screen | Redirect to facebook page in new tab with share screen | FAIL | LNMNhật | 2021-12-23
Function 04: View & Edit user profile | UC04
UC04 | UI11 | View profile | 1. Sign Up (Skip if you already have an account) 2. Login (username: "anhkhoa24082001@gmail.com", password: "123456") 3. Click on the bottom area of the navbar | User view account information | Can't display the user's learned courses, can't show the completion progress | FAIL | PAKhoa | 2021-12-23
UC04 | UI12 | Edit profile | 1. Sign Up (Skip if you already have an account) 2. Login (username: "anhkhoa24082001@gmail.com", password: "123456") 3. Click on the bottom area of the navbar 4. Click "Edit Profile" 5. Change First Name 6. Click Save | User wants to change first name | Name has been changed and there are no errors | Pass | PAKhoa | 2021-12-23
UC04 | UI13 | Edit profile | 1. Sign Up (Skip if you already have an account) 2. Login (username: "anhkhoa24082001@gmail.com", password: "123456") 3. Click on the bottom area of the navbar 4. Click "Edit Profile" 5. Click "Security" 6. Write Oldpassword (123456) 7. Wrte New Pass and Confirm new Pass (123457) 8. Click Update Password | User wants to change Password | Password does not change | FAIL | PAKhoa | 2021-12-23
Function 05: View & Edit role for user | UC05
UC05 | UI14 | Delete "admin" user | 1. Sign Up (Skip if you already have an account) 2. Login with admin account (username: "quannguyenthanh558@gmail.com", password: "123456") 3. Click on admin page on navbar 4. Choose 1 user in role 'admin' 5. Click "Delete" icon | "Delete" icon is disable and this user can not be delete | "Delete" icon is disable and this user can not be delete | Pass | NTQuân | 2021-12-23
UC05 | UI15 | Delete "normal" user | 1. Sign Up (Skip if you already have an account) 2. Login with admin account (username: "quannguyenthanh558@gmail.com", password: "123456") 3. Click on admin page on navbar 4. Choose 1 user not in role 'admin ' 5. Click "Delete" icon | "Delete" icon is activate and this user deleted | "Delete" icon is activate and this user deleted | Pass | NTQuân | 2021-12-23
UC05 | UI16 | Set role for "admin" user | 1. Sign Up (Skip if you already have an account) 2. Login with admin account (username: "quannguyenthanh558@gmail.com", password: "123456") 3. Click on admin page on navbar 4. Choose 1 user in role 'admin ' 5. Click "setting" icon 6. Change any role (here is "sensor") | "Setting" icon is disable and this user can not be change role by another admin | "Setting" icon is disable and this user can not be change role by another admin | Pass | NTQuân | 2021-12-23
UC05 | UI17 | Set role for "normal" user | 1. Sign Up (Skip if you already have an account) 2. Login with admin account (username: "quannguyenthanh558@gmail.com", password: "123456") 3. Click on admin page on nav bar 4. Choose 1 user not in role 'admin ' 5. Click "setting" icon 6. Change any role (here is "sensor") | "Setting" icon is activate and this user's role is change into "sensor" | "Setting" icon is activate and this user's role is change into "sensor" | Pass | NTQuân | 2021-12-23
UC05 | UI18 | Search user | 1. Sign Up (Skip if you already have an account) 2. Login with admin account (username: "quannguyenthanh558@gmail.com", password: "123456") 3. Click "Admin Page" on navbar 4. Fill any name in search bar (here is "Khoa") | User area will show every user has word "Khoa" in name | User area will show every user has word "Khoa" in name | Pass | NTQuân | 2021-12-23